## Sheet1
Receptionist Robot
Task | Description | Estimated Duration
Completed Tasks
Specification document | Defines the robot’s functional and technical requirements. | ✅ 1 week
Hardware selection | Choosing components like Jetson Nano, motors, LiDAR, sensors, and power supply. | ✅ 3 days
Remaining Tasks
Setup & Configuration
Installing & setting up OS on Jetson Nano | Installing OS, configuring drivers, and preparing the environment for development. | 2 - 3 days
Multimodal Interaction
Speech Recognition & Chatbot | Developing a chatbot for human-robot interaction. | 1 - 2 weeks
Integrating speaker & microphone on Jetson | Connecting and configuring audio devices for speech input and response. | 1 week
Face Recognition | Implementing a system to detect and recognize faces for user identification. | 1 - 2 weeks
Camera interaction with Jetson Nano | Setting up and optimizing the camera for facial recognition and environment analysis. | 1 week
Touchscreen interaction | Creating a user interface for interaction via touch commands. | 1 week
Integration & Navigation
Full implementation on Jetson Nano | Integrating all software modules onto the Jetson Nano. | 1.5 - 2 weeks
Navigation system (ROS integration & SLAM) | Implementing ROS and SLAM for localization and autonomous movement. | 3 - 4 weeks
Lidar interaction | Using LiDAR for mapping, obstacle detection, and navigation. | 1 - 2 weeks
Assembling everything into the robot | Assembling and testing all hardware and software components. | 2 weeks